## Program Roll Out Plan
Task | Assignee | Dependency (If any) | Start Date | End Date | Status | Remarks (If any)
I. Pilot Kick-Off
Meeting to initiate discussion on Pilot Preparation | Prashanth | None | 4th April | 6th April | Completed
Identification of SPOCs from Department for Pilot | Prashanth | None | 4th April | 6th April | Completed | Shubhranshu (Functional) + Anil ( Technical)
Identification of SPOCs from 2 ULBs for Pilot Preparation (For logistics support, training, driving data entry, dissemination of IEC material etc. ) | Prashanth | None | 4th April | 6th April | Completed | Subrat - Dhenkanal Madhusmita - Jatani
Communication to Department and ULBs regarding timeline | Shivani | Confirmed with the department. To be additionally notified through a letter | 23rd April | 2nd May | Completed
II. Governance Set-Up
Agree on Roles and Responsibilities for Stakeholders | Shivani | To be shared in a letter with the department, department to approve/ suggest modifications | 23rd April | 27th April | In Progress
Sign off on Pilot Success Metrics | Shivani | To be shared in a letter with the department, department to approve/ suggest modifications | 23rd April | 3rd May | In Progress
Sign off on Adoption Metrics from Department | Shivani | To be shared in a letter with the department, department to approve/ suggest modifications | 23rd April | 3rd May | In Progress
Agree on review and monitoring frequency and stakeholders with Department | Shivani | To be shared in a letter with the department, department to approve/ suggest modifications | 23rd April | 3rd May | In Progress
Agree on review and monitoring frequency and stakeholders with ULBs | Shivani | To be shared in a letter with the department, department to approve/ suggest modifications | 23rd April | 3rd May | In Progress
Agree on escalation matrix (ULB Level, Department Level) | Shivani | To be shared in a letter with the department, department to approve/ suggest modifications | 23rd April | 3rd May | In Progress
On-boarding of PMU for supporting adoption and monitoring on-ground | Shivani | Subhranshu, HUDD SPOC to support in executing this | 23rd April | 3rd May | In Progress | Department in the process of on-boarding an EY team for this
III. Institution of Help Desk
Set-up of L1 Helpdesk for Go-Live - Identification of Personnel | Arindam | To be executed by the department | 15th May | 25th May | Not Initiated | Already agreed with the department
Training of Helpdesk Personnel | Nirbhay | Nominated individuals to be made available for training | 15th May | 18th May | Not Initiated
Setting up of a Ticketing System | Arindam | To be facilitted by eGov team(JIRA free version) | 4th May | 24th May | Not Initiated
Develop and share an SOP for triaging | Arindam | None | 26th Arpil | 28th April | Completed
Escalation Matrix for functional/ technical queries | Arindam | None | 26th April | 28th April | Completed
IV. User Training & UAT
Creation of Training Plan | Shivani | None | 24th April | 2nd May | Completed
Venue: SUDA Conference Hall |  |  | 15th May | 18th May | NA
Trainers/ UAT Drivers: Nirbhay and Arindam |  |  | 15th May | 18th May | NA
Facilitators: Sourav, Shivani and Prashanth |  |  | 15th May | 18th May | NA
Master Trainers (~15 members) 1. 5 members from UMC MUKTA team in Bhubaneshwar 2. 2 IT Resources from UMC Head-Office 3. 4 City Mission Managers (CMMs) 4. From HUDD - Anil and Ashutosh 5. 2 MIS Team members nominated to constitute the Helpdesk |  |  | 15th May | 18th May | NA
MUKTASoft Users (~10 members) 1. ULB Employees (EO, JE, AE, ME, MUKTA Team - Implementation Expert, Program Coordinator, Accountant, MIS Team Member) 2. SHG Members (President & Secreatary from 4 SHGs where 2 SHGs will be from Dhenkanal and 2 from Jatani) |  |  | 15th May | 18th May | NA
Devices Required 1. Laptop/ Desktop: Windows Devices with alteast Windows 10 Pro and Chrome browser (latest version) 2. Mobiles: Android Devices with Android 10 for CBOs to download app or phone with Chrome Browser (latest version) for ULB staff to use the app on phone instead of laptop/ desktop |  | Shubhranshu to support on ground. | 15th May | 18th May | NA
Training Day1 |  | Availability of Trainees + Required Devices | 22nd May | 22nd May | NA
9:00 am - 9:30 am Registration |  |  | NA | NA | NA
9:30 am -10:30 am Demo |  |  | NA | NA | NA
10:30 am - 11:00 am Tea Break |  |  | NA | NA | NA
11:00 am - 1:00 pm Hands-on Training Session 1 (Project, Estimate) |  |  | NA | NA | NA
1:00 pm -2:00 pm Lunch |  |  | NA | NA | NA
2:00 pm - 4:00 pm Hands-on Training Session 2 (Work Order,Muster Roll, Purchase Bill, Payment Advice) |  |  | NA | NA | NA
4:00 pm- 4:30 pm Tea Break |  |  | NA | NA | NA
4:30 pm- 5: 30 pm Hands-on Training Session 3 (CBO Portal) |  |  | NA | NA | NA
Training Day 2 |  |  | 23rd May | 23rd May | NA
9:30 am -11:00 am Hands-on Training continues |  |  | NA | NA | NA
11:00 am - 11:30 am Tea Break |  |  | NA | NA | NA
11:30 am - 1:00 pm Q & A, Feedback, Preparation for UAT (Test case handouts distributed based on Roles) |  |  | NA | NA | NA
1:00 pm - 2:00 pm Lunch |  |  | NA | NA | NA
2:00 pm - 4:00 pm UAT Session 1 |  |  | NA | NA | NA
4:00 pm- 4:30 pm Tea Break |  |  | NA | NA | NA
4:30 pm - 5:30 pm UAT Session 2 |  |  | NA | NA | NA
Training Day 3 |  |  | 24th May | 24th May | NA
9:30 am - 11:00 am UAT Session 3 |  |  | NA | NA | NA
11:00 am - 11:30 am Tea Break |  |  | NA | NA | NA
11:30 am - 1:00 pm UAT Session 4 |  |  | NA | NA | NA
1:00 pm - 2:00 pm Lunch |  |  | NA | NA | NA
2:00 pm - 4:00 pm UAT Session 5 |  |  | NA | NA | NA
4:00 pm- 4:30 pm Tea Break |  |  | NA | NA | NA
4:30 pm - 5:30 pm UAT Session 6 |  |  | NA | NA | NA
Training Day 4 |  |  | 25th May | 25th May | NA
9:30 am - 11:00 am UAT Session 7 |  |  | NA | NA | NA
11:00 am - 11:30 am Tea Break |  |  | NA | NA | NA
11:30 am - 1:00 pm UAT Session 8 |  |  | NA | NA | NA
1:00 pm - 2:00 pm Lunch |  |  | NA | NA | NA
2:00 pm - 4:00 pm (Bugs, Enhancements, Feedback Collection and Prioritization) |  |  | NA | NA | NA
4:00 pm- 4:30 pm Tea Break |  |  | NA | NA | NA
4:30 pm - 6:00 pm Feedback , Quiz on Training and UAT, Closure |  |  | NA | NA | NA
Creation of Training Assets (User Manuals, FAQs and Demo Videos) | eGov Team | UMC to Support on Translation & Design | 26th April | 19th May | In Progress
User Manuals | Nirbhay |  | 26th April | 5th May | In Progress
FAQs | Nirbhay
Demo Videos | Nirbhay |  | 11th May | 13th May | Not Initiated | Will be ready by Go-Live
Translation and Printing of Training Assets | UMC -Pranati | Assets to be shared with UMC Team as and when completed by us to start translation | 6th May | 19th May | Not Initiated
Training Delivery and UAT | eGov Team | Trainees and Devices to be available | 15th May | 19th May | Not Initiated
Facilitate Training | Nirbhay + Arindam |  | 15th May | 19th May | Not Initiated
Gather Feedback on Training | Program Team | Feedback Questionnaire to be Translated | 19th May | 19th May | Not Initiated
UAT Sign-Off | Program Team |  | 19th May | 19th May | Not Initiated
Plan Refresher Training (Tentatively 3-4 weeks later ) | Program Team | To be planned based on feedback | 15th June | 17th June | Not Initiated
V. IEC Activties (More compreshensive IEC to be planned with Department Support for V1.2 Go-live)
A. Printables |  |  | 3rd May | 31st May
Provide Content for 1 Flier (App Specific) | Satwinder | UMC to Support on Translation & Design | 3rd May | 12th May | Not Initiated | Initial review to be planned with UMC to broad concept and content by 3-4th May
Provide Content for 1 Poster (App + MUKTA) | Satwinder | UMC to Support on Translation & Design | 3rd May | 12th May | In Progress | Initial review to be planned with UMC to broad concept and content by 3-4th May
Design, Translation and Printing of Flier and Poster | Shivani | UMC to Support on Translation, Design and Printing | 15th May | 25th May | Not Initiated
Dissemination of IEC Content | Sourav | ULB SPOC to support in execution | 27th May | 31st May | Not Initiated
Press Release | Prashanth | To be discussed with HUDD, at what stage this will be planned | To be decided | To be decided | Not Initiated | HUDD wanted this to be done after JIT Integration initially
B. Social Media |  |  | 31st May | 2nd June
1 Tweet from HUDD Twitter Account | Saurav | Satwinder to help in drafting content, department to approve | 1st June | 1st June | Not Initiated | Draft Content during UAT, Post between UAT and Go-Live
1 Tweet each from ULBs (Municipality Accounts) | Saurav | Satwinder to help in drafting content, department to approve | 1st June | 1st June | Not Initiated | Draft Content during UAT, Post between UAT and Go-Live
Post from HUDD FB Account | Saurav | Satwinder to help in drafting content, department to approve | 1st June | 1st June | Not Initiated | Draft Content during UAT, Post between UAT and Go-Live
1 Post each from ULBs (Municipality Accounts) FB Accounts | Saurav | Satwinder to help in drafting content, department to approve | 1st June | 1st June | Not Initiated | Draft Content during UAT, Post between UAT and Go-Live
C. Messages/ Whatsapp |  |  | 31st May | 31st June
Messages blast on existing CBO/ ULB whatsapp group on Launch in Production | Saurav | Satwinder to help in drafting content. Draft Content during UAT, Post between UAT and Go-Live. | 31st May | 30th June | Not Initiated | Weekly blasts between during the 1 month window
- Message 1 - (Snippet of Training Video) | Saurav | Satwinder to help in drafting content. Draft Content during UAT, Post between UAT and Go-Live. | 31st May | 30th June | Not Initiated | Weekly blasts between during the 1 month window
- Message 2 - (Recognition and Incentivisation, may include posting pictures for work completed by SHGs etc.) | Saurav | Satwinder to help in drafting content. Draft Content during UAT, Post between UAT and Go-Live. | 31st May | 30th June | Not Initiated | Weekly blasts between during the 1 month window
VI. Change Management Plan
People / Behavioural Management
Training Plan (Covered in Section IV above) | Shivani | None | 26th April | 3rd May | Completed
IEC Plan (Covered in Section V above) | Shivani | None | 26th April | 3rd May | Completed
Incentives | TBD
Officiial notifications to gradually restrict manual practices to 2 ULBs: 1. Only MUKTASoft generated muster rolls will be approved starting July 1st (for projects approved after go-live date) 2. Editing of attendance should be undertaken only for last 2 weeks starting July 15th (for projects approved after go-live) and the window for editing attendance will be limited to 1 week with launch of v1.1 | Sourav |  |  |  |  | To be taken up fate V1.2 launch
Technical Change Management
Gather Feedback After Go-Live (Bi-weekly calls with CBOs and ULB members from 2 ULBs) | eGov Team | None | 8th June | 15th July | Not Initiated | Ongoing Activity. Reflected in the Meeting Cadence
Plan for Enhancements/ Upgrades/ Changes (Detailed Technical Effort to be Planned) | Arindam | Once we have inputs from UAT this can be estimated | 26th May | 30th May | Not Initiated
Cadence for Identifying and Prioritizing Enhancements | Shivani | None | 23rd April | 3rd May | Completed | Reflected in the Meeting Cadence
VII. Adoption Plan
Creation of User Training Plan (Covered in Section IV above) | Shivani | None | 24th April | 2nd May | Completed
Institution of Help Desk Institution (Covered in Section III above) | Arindam | Support required from department to set up tool, resources. | 26th April | 26th May | In Progress | Included as part of Issue Resolution Matrix; Agreement taken from the department on this
Establish Program Governance Structure | Shivani | To be shared in a letter with the department, department to approve/ suggest modifications | 23rd April | 3rd May | Completed
Establish Review Cadences | Shivani | To be shared in a letter with the department, department to approve/ suggest modifications | 23rd April | 3rd May | Completed
Incentives | TBD
Roll -Out Dashboard / Scripts | Arindam | To be initiated on finalization of success metrics | 8th May | 15th May | Not Initiated

## Additional Inputs (hidden)
Pilot | 45 days
Pilot Success Criteria define and agree | Bill Approval, Tech Sanction, Financial Sanction, Muster Roll, Attendance
Go-Live Definition
Set-up cadence for review with ULBs (ideally weekly)
On ground presence | Sourav
SUJOG Help Desk & Ticketing Tool
Roll Out Dashboard | Metrics for Roll-Out Success | Scripts for getting this information to monitor UAT Progress
Change Management Plan | Tech (Bugs, Features, Enhancements) + People (IEC, Training, Incentives)
Bugs and Features to be closed within Pilot time frame
Roles and Responsobilities | Letter (Draft)
Users as master trainers -explore, can be more useful
IEC | SMS Blast, Use Whatsapp groups to share success stories, training videos
Training | Make the demo video publicly available
Security Audit | Reuse NUDM certificate (Sathish P)
Escalation Matrix | Enhancements - who takes a call on whether it needs to be built
IEC Collateral | Confirm to begin after Drop 1 or after Drop 2 & 3
Integration | Reports that absolve/ prove that no issues created from our team (Impel )
Master Trainers | Monthly refreshers
User to Role Mapping | Clear definition of role mapping

## Adoption Metrics (hidden)
Indicative Adoption Metrics
Faster Approvals | TAT
Faster Payments | TAT
Registrations
CBO + Wage Seeker | Number
Project Metrics
Contracts Status | Created->In Progress-> Completed
Payments to Wage Seekers, CBOs and Vendors
Project Status | On Track ¦ Delayed
Attendance | Weekly as per guidlines or not?

## UAT Planning (hidden)
Employees
CBOs
Roughly 3 days
1 day Buffer